## AEWA Secretariat PoW 2026-2028
Ver. 12 Mar 2026
Objective: | Promote, facilitate and support a coordinated and concerted approach to the implementation of AEWA in line with its provisions and the decisions of the Meeting of the Parties | [6 empty] | Year: | 2026-02-01 |  |  | 2026-05-01 |  |  | 2026-08-01 |  |  | 2026-11-01 |  |  | 2027-02-01 |  |  | 2027-05-01 |  |  | 2027-08-01 |  |  | 2027-11-01 |  |  | 2028-02-01 |  |  | 2028-05-01 |  |  | 2028-08-01 |  |  | 2028-11-01 |  |  | 2029-02-01 |  |  | 2029-05-01 |  |  | 2029-08-01 |  |  | 2029-11-01 |  |  | 2030-02-01 |  |  | 2030-05-01 |  |  | 2030-08-01 |  |  | 2030-11-01 |  |  | 2031-02-01 |  |  | 2031-05-01 |  |  | 2031-08-01 |  |  | 2031-11-01 |  |  | 2032-02-01 |  |  | 2032-05-01 |  |  | 2032-08-01 |  |  | 2032-11-01 |  |  | 2033-02-01 |  |  | 2033-05-01 |  |  | 2033-08-01 |  |  | 2033-11-01 |  |  | 2034-02-01 |  |  | 2034-05-01 |  |  | 2034-08-01
PoW Start Date: | 2026-01-01 | [6 empty] | Quarter: | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3
Title: | AEWA Secretariat PoW 2026-2028 | [6 empty] | Month: | time axis 2026-01-01 to 2034-09-01
# | Activity | Priority | Assigned To | Need funds | Start | End | Days | Status
Outcome 1 | The governing and subsidiary bodies of the Agreement perform their functions and deliver on their respective mandates (Articles VI, VII & VIII; Res. 2.6, 9.7, 9.8 & 9.10)
Output 1.1 | Meeting of the Parties (MOP): MOP10 has been convened and concluded (Articles VI & VIII; Res. 9.10)
Activity 1.1.1 | Convene and service MOP10, including arrange and secure the hosting, funding and logistical arrangements (Articles VI & VIII(a); Res. 9.10, OP1-4) | 1 | SD, ML, EPM, FK, CL, BL, MTK, JD, BD, DS, SH | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2027-07-01 to 2028-12-01
Activity 1.1.2 | Produce and/or facilitate the production of the MOP10 substantive content (Articles VI & VIII(a) & (f)) | 1 | SD, ML, CL, FK, EPM, JD | Partially | 2027-07-01 | 2028-12-31 | 392 | bar: 2028-04-01 to 2028-10-01; 2028-12-01
Output 1.2 | Standing Committee (StC): the StC has performed its tasks and mandates as assigned by the MOP (Res. 2.6, 4.6 & 9.7, other relevant Res.)
Activity 1.2.1 | Convene and service the meetings of the StC as well as its operations between its meetings (Res. 2.6 & 9.7) | 1 | SD, CL, MTK, JD | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2026-01-01 to 2026-03-01; 2026-05-01 to 2026-08-01; 2027-05-01 to 2027-08-01; 2028-05-01 to 2028-08-01; 2028-11-01 to 2028-12-01
Activity 1.2.2 | Produce and/or facilitate the production of substantive content for the StC meetings, including administering the AEWA Waterbird Conservation Award nomination procedure (Res. 2.6 & 9.7) | 1 | SD, CL, JD | (Partially) | 2026-01-01 | 2028-12-31 | 782 | bar: 2026-01-01 to 2026-02-01; 2026-05-01 to 2026-07-01; 2027-05-01 to 2027-07-01; 2028-05-01 to 2028-07-01; 2028-10-01 to 2028-12-01
Activity 1.2.3 | Assist the StC in undertaking the Implementation Review Process (IRP) (Res. 4.6) | 2 | SD, ML, EPM | Yes | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Output 1.3 | Technical Committee (TC): the TC has delivered on its workplan for 2026-2028 (Articles VII & VIII; Res. 9.8)
Activity 1.3.1 | Convene and service the meetings of the TC as well as its operations between its meetings (Articles VII & VIII(a); Res. 9.8, OP3) | 1 | ML, SD, FK, JD | (Partially) | 2026-01-01 | 2028-12-31 | 782 | bar: 2026-01-01 to 2026-05-01; 2026-12-01 to 2027-04-01; 2027-12-01 to 2028-04-01; 2028-12-01
Activity 1.3.2 | Produce and/or facilitate the production of substantive content for the TC meetings (Articles VII & VIII(a); Res. 9.8, OP3), in particular the following TC Workplan 2026-2028 tasks: | 1 | ML, SD, FK, EPM, JD | Partially | 2026-01-01 | 2028-06-30 | 652 | bar: 2026-01-01 to 2026-04-01; 2026-12-01 to 2027-03-01; 2027-12-01 to 2028-03-01; 2028-06-01
| Task 1.3: Review of Table 1 in Annex 3 to the Agreement. Prepare proposals for revision of Table 1 in Annex 3 for submission to MOP10 (Linked to activity 2.2.1) | 1 | SD, ML | Yes | 2028-01-01 | 2028-04-30 | 85 | bar: 2028-01-01 to 2028-04-01
| Task 1.4: Review of intended proposals by Parties for amendments to the Agreement (circulate a call for submission to TC before MOP10) | 1 | ML, JD | No | 2027-10-01 | 2028-03-31 | 131 | bar: 2028-03-01
| Task 1.7: Guidance on Favourable Reference Values | 1 | ML, SD | Yes | ?
| Task 1.8: Guidance on maintaining Favourable Reference Population (FRP) | 1 | ML, SD, BL | Yes | ?
| Task 1.9: Guidance on the application of definitions of AEWA Table 1 categories | 1 | ML, SD | No | ?
| Task 1.10: Criteria for listing of re-established populations | 1 | ML, SD | No | ?
| Task 2.2: Evaluation Report Template for International Species Action and Management Plans | 1 | ML, SD | No | ?
| Task 2.4: Guidance on adaptive harvest management. Prepare simple guidance drawing on existing knowledge, experience and processes. | 2 | BL, ML, SD | Yes | ?
| Task 4.5: Harvest data estimates. Build a framework for waterbird harvest data collection at flyway level (EU project grant, PCA4) | 1 | EPM, SD, JD | Secured | 2026-03-01 | 2028-06-30 | 610 | bar: 2028-06-01
Outcome 2 | The implementation of the Agreement and its Strategic Plan are reported and monitored (Article V; Res. 9.2)
Output 2.1 | National Reporting: national reports to MOP10 are submitted and analysed and initial preparations for reporting to MOP11 are made (Article V.1(c); Res. 9.2 & 9.8)
Activity 2.1.1 | Secure funding for and facilitate transition to the new Online Reporting System (ORS) (Res. 9.2, OP22) | 1 | EPM, FK, SD | Yes | 2026-02-01 | 2026-12-31 | 239 | bar: 2026-12-01
Activity 2.1.2 | Provide targeted training to National Focal Points and Designated National Respondents in advance of launching the MOP10 reporting process (Res. 9.2, OP14) (EU project grant, PCA3) (Partially dependent on Activity 2.1.1) | 1 | EPM, ML, SD, BD, FK, DS | Secured | 2026-02-01 | 2028-03-31 | 565 | bar: 2026-07-01 to 2026-12-01; 2027-07-01 to 2027-11-01; 2028-01-01 to 2028-03-01
Activity 2.1.3 | Launch and facilitate the reporting to MOP10 (Module 1: population status and Module 2: general NR), incl. assisting the TC in compiling guidance on Module 1 and revision, amendment and enhancement of Module 2 template, as necessary (Res. 9.8 & TC WP task 8.3) (Linked to Activity 1.3.2) | 1 | EPM, SD, BD, DS | Partially | 2026-03-01 | 2028-04-30 | 565 | bar: 2026-03-01 to 2026-06-01; 2026-10-01 to 2027-04-01; 2028-04-01
Activity 2.1.4 | Secure the funding for and outsource the compilation of analysis of the national reports submitted to MOP10 (Res. 9.2, OP21) | 2 | EPM, SD | Yes | 2027-07-01 | 2028-07-31 | 283 | bar: 2028-01-01 to 2028-05-01; 2028-07-01
Activity 2.1.5 | Assist the TC in preparing the draft national report format for MOP11 (2028-2030), which format shall be aligned with the draft Strategic Plan 2029-2037, as well as any other modules for submission to MOP11 (Res. 9.8 & TC WP task 8.3) (Linked to Activity 1.3.2) | 1 | EPM, SD, ML, FK | No | 2027-07-01 | 2028-06-30 | 262 | bar: 2027-11-01 to 2028-06-01
Activity 2.1.6 | Plan for establishing a sustained approach to National Reporting training to be rolled out with the 3rd Strategic Plan 2029-2037 (Res. 9.2, OP15) | 2 | EPM, SD, ML, FK | No | 2027-07-01 | 2028-06-30 | 262 | bar: 2028-06-01
Output 2.2 | International Reviews: prioritised international reviews as per paras 7.4 & 7.5 of AEWA’s Annex 3 have been compiled and submitted to MOP10 (AEWA Action Plan, paras 7.4 & 7.5; Res. 9.8)
Activity 2.2.1 | Secure the funding for and outsource the compilation of the 10th edition of the Conservation Status Report (CSR10) in consultation with the TC (AEWA Annex 3, paras 7.4 & 7.5; Res. 9.2, OP3) | 1 | SD, ML, JD | Yes | 2026-09-01 | 2028-06-30 | 479 | bar: 2027-01-01 to 2028-04-01; 2028-06-01
Activity 2.2.2 | Secure the funding for and outsource the compilation of an updated Review on the status of introduced non-native waterbird species and hybrids thereof in consultation with the TC (AEWA Annex 3, paras 7.4 & 7.5) | 2 | ML, SD, JD | Yes | 2026-09-01 | 2028-06-30 | 479 | bar: 2028-06-01
Output 2.3 | Strategic Plan evaluation: the final evaluation of the implementation of the Strategic Plan 2019-2027 has been submitted to and informed the decisions of MOP10 (Res. 9.2)
Activity 2.3.1 | Assist the TC in improving the assessment of Strategic Plan indicators (Res. 9.8 & TC WP task 8.3) (Linked to Activity 1.3.2) | 2 | EPM, SD | No | 2026-03-01 | 2026-06-30 | 87 | bar: 2026-03-01 to 2026-06-01
Activity 2.3.2 | Support the StC is compiling the final evaluation Report on the Implementation of the Strategic Plan 2019-2027 (Res. 9.2, OP4) | 2 | SD, EPM, ML | Yes | 2028-01-01 | 2028-08-31 | 174 | bar: 2028-06-01 to 2028-08-01
Output 2.4 | AEWA’s contribution to relevant global frameworks: an assessment of AEWA’s contribution has been compiled and submitted to MOP10 (Res. 9.8 & TC WP task 8.5)
Activity 2.4.1 | Assist the TC in compiling the assessment of AEWA’s contributions to relevant global frameworks (Res. 9.8 & TC WP task 8.5) (Linked to Activity 1.3.2) | 2 | ML, SD, EPM, FK | No | 2027-07-01 | 2028-04-30 | 217 | bar: 2028-04-01
Outcome 3 | The coherence of AEWA mandates and legal provisions is strengthened (Res. 9.1 & 9.2)
Output 3.1 | AEWA text and annexes: The official text and annexes are up to date in line with the MOP9 amendments (Res. 9.1)
Activity 3.1.1 | Working with the Depository, update AEWA Annexes 2 and 3 in the four official languages of the Agreement, and where feasible other languages, and publish them on the AEWA website (Res. 9.1, OP6) | 1 | CL, SD, SH, BL | (No) | 2026-01-01 | 2026-10-31 | bar: 2026-01-01 to 2026-03-01
Output 3.2 | Consolidation of MOP resolutions: MOP10 has adopted consolidated versions of all past MOP resolutions (Res. 9.2)
Activity 3.2.1 | Consolidate all previously adopted MOP resolutions and submit to MOP10 for adoption (Res. 9.2, OP10) | 1 | CL, SD, ML | Partially | 2026-02-01 | 2026-12-31 | 239 | bar: 2026-04-01 to 2026-09-01; 2026-12-01
Output 3.3 | Optimisation of the AEWA Action Plan: MOP10 has adopted amendments to Annex 3 of the Agreement (Res. 9.1)
Activity 3.3.1 | Review the Action Plan in Annex 3 to the Agreement and suggest possible optmisations as well as compile proposal to MOP10 for amendments of Annex 3 (Res. 9.1, OP7) | 1 | ML, SD | Partially | 2026-02-01 | 2026-12-31 | 239 | bar: 2026-04-01 to 2026-09-01; 2026-12-01
Outcome 4 | AEWA implementation is guided by strategically prioritised mid-term objectives and targets in line with AEWA’s provisions (Articles III, IV & VI)
Output 4.1 | 3rd AEWA Strategic Plan for the period 2029-2037: MOP10 has adopted the 3rd Strategic Plan for the period 2029-2037 (Res. 9.2)
Activity 4.1.1 | Secure the funding for and support the StC in developing a draft Strategic Plan for the period 2029-2037 and in submitting it for consideration and adoption by MOP10 (Res. 9.2, OP6 & 8) | 1 | SD, ML, EPM, FK, CL, JD, BD | Yes | 2026-07-01 | 2027-12-31 | 393 | bar: 2027-01-01 to 2027-09-01; 2027-12-01
Output 4.2 | Supporting products and mechanisms associated with the 3rd Strategic Plan: relevant products and mechanisms have been developed or strengthened to support the implementation of the 3rd Strategic Plan 2029-2037 (Res. 9.2 & 9.6)
Activity 4.2.1 | Support the StC in compiling guidance on relevant overarching and cross-cutting issues to be identified with respect to the Strategic Plan implementation (Res. 9.2, OP6) | 2 | CL, ML, FK, SD | Yes | 2027-09-01 | 2028-08-31 | 262 | bar: 2028-08-01
Activity 4.2.2 | Support the StC in conceptualising a targeted, simplified and direct mechanism or approach to support implementation based on the Strategic Plan 2029-2037 to replace the Plan of Action for Africa and submitting it to MOP10 for consideration (Res. 9.2, OP7) (Linked to Activity 4.2.3) | 1 | EPM, SD, ML, CL | Partially | 2027-07-01 | 2028-06-30 | 262 | bar: 2027-09-01 to 2028-02-01; 2028-06-01
Activity 4.2.3 | Develop measures for the continued provision of guidance and assistance to Contracting Parties through their National Focal Points and other designated personnel, with a view to strengthening their knowledge, understanding, and capacity for the effective implementation of AEWA, particularly in the context of the Strategic Plan 2029-2037 (Res. 9.2, OP9) (Linked to Activity 4.2.2) | 1 | EPM, SD, ML, CL | Partially | 2027-07-01 | 2028-06-30 | 262 | bar: 2027-09-01 to 2028-02-01; 2028-06-01
Activity 4.2.4 | Compile a refined overview of Secretariat’s roles, responsibilities and tasks to focus its work on facilitating the effective and efficient implementation of the Agreement and its Strategic Plan 2029-2037 (Res. 9.2, OP11) (Dependent on Activities 3.2.1, 3.3.1, 4.1.1, 4.2.2, 4.2.3, 4.2.5 & 4.2.6) | 1 | SD, ML, CL | No | 2027-09-01 | 2028-03-31 | 153 | bar: 2027-11-01 to 2028-03-01
Activity 4.2.5 | Consult the StC in the development of a modified [SGF] or alternative/supplementary mechanism for funding AEWA relevant projects for eligible Parties and the submission to MOP10 (Article V.3; Res. 9.2, OP25) | 2 | EPM, SD, ML | Partially | 2026-04-01 | 2027-04-30 | 283 | bar: 2027-04-01
Activity 4.2.6 | Support the StC in developing a comprehensive modus operandi for the IRP and a proposal for a broader framework that will support Parties in complying with AEWA for submission to MOP10 (Res. 9.2, OP26) | 2 | ML, SD | Partially | 2026-04-01 | 2027-04-30 | 283 | bar: 2027-04-01
Activity 4.2.7 | Secure the funding for and work with the StC and TC on producing a CEPA work plan alongside the draft Strategic Plan (2029-2037) to support the achievement of its goals (Res. 9.6, OP2 & 3) (Linked to Output 10.2) | 2 | FK, SD, ML, EPM | Yes | 2027-09-01 | 2028-08-31 | 262 | bar: 2028-08-01
Outcome 5 | AEWA implementation benefits from a strengthened science-policy interface (Res. 9.2)
Output 5.1 | AEWA science-policy interface: MOP10 has adopted an improved science-policy interface (Res. 9.2)
Activity 5.1.1 | Assist the StC and the TC in reviewing AEWA’s workflow in the light of science-policy interface models under other MEAs and developing and submitting to MOP10 a proposal for improving the AEWA science-policy interface (Res. 9.2, OP23) (Linked to Activities 1.2.2 & 1.3.2) | 2 | SD, ML | Partially | 2026-05-01 | 2028-04-30 | 521 | bar: 2028-04-01
Outcome 6 | Priority species/populations are covered by effectively implemented Species Action Plans and adaptive harvest management regimes are in place and being effectively implemented in the framework of Species Action or Management Plans (AEWA Annex 3, paras 2.1.1, 2.2.1 & 4.3.4; Strategic Plan targets 1.2 & 2.4)
Output 6.1 | Species action and management planning and implementation: the development, harmonisation and implementation of Species Action and Management Plans are coordinated (AEWA Annex 3, paras 2.2.1 and 4.3.4; Strategic Plan targets 1.2 & 2.4; Res. 5.8, 6.4, 6.8, 6.9, 7.5, 8.4 & 9.3)
Activity 6.1.1 | Provide structured support to International Working and Expert Group Coordinators by developing dedicated webpages and online workspaces, providing training through a Coordinators’ Forum, promoting awareness and showcasing successes in relevant fora, and developing toolkits of materials, elements of which are trialed in at least one International Species Working Group (AEWA Action Plan para 2.2.1; Res. 8.4, OP 24-25) (EU project grant, PCA4) | 1 | ML, EPM, JD, BD, DS, BL, SH | Secured | 2026-02-01 | 2028-12-31 | 760 | bar: 2026-07-01 to 2026-12-01; 2027-06-01 to 2027-12-01; 2028-12-01
Activity 6.1.2 | Administer the ongoing project to mitigate crop damage by, and poisoning of, Grey Crowned Cranes, thereby supporting implementation of the AEWA Grey Crowned Crane International Single Species Action Plan (GCC ISSAP, as adopted through Res. 6.8 & extended through Res. 9.3) (EU project grant, PCA3) | 1 | EPM, ML, BD | Secured | 2026-01-01 | 2028-08-31 | bar: 2028-09-01
Activity 6.1.3 | Facilitate the operations of the European Goose Management Platform and implementation of the International Species Action and Management Plans and associated processes which fall under its remit (Res. 6.4, OP9 & Res. 9.3, OP21) (regular annual voluntary contributions by EGMP Range States) | 1 | BL, ML, SH | (Regular annual voluntary contributions) | 2026-01-01 | 2028-12-31 | 782 | bar: 2026-01-01 to 2026-06-01; 2027-01-01 to 2027-06-01; 2028-01-01 to 2028-06-01; 2028-12-01
Activity 6.1.4 | Facilitate the evaluation, and, where necessary, update or revision of the identified 11 ISAPs and encourage Range States to actively engage while following a recommended prioritisation of ISAPs by the TC (Res. 9.3, OP13) | 3 | ML | Yes | ?
Activity 6.1.5 | Disseminate the list of priority populations for action and management planning to Contracting Parties, and to make it available on the AEWA website, once this list has been updated by the TC (Res. 9.3, OP19) | 2 | ML, FK, DS | No | 2026-05-01 | 2026-05-30 | 21 | bar: 2026-05-01
Activity 6.1.6 | Address the current gaps in the international coordination of ISAPs by identifying suitable organisations to coordinate International Species Working Groups and explore opportunities for joint coordination of ISAPs and for other types of collaboration between coordination mechanisms (Res. 9.3, OP16) | 3 | ML | Yes | ?
Activity 6.1.7 | Convene a meeting of key stakeholders to determine a strategic, realistic and cost-effective way to enhance implementation of AEWA ISAPs (Res. 8.4, OP 24) | 2 | ML, BL, JD | Partially | ?
Outcome 7 | A coherent and comprehensive flyway network of protected areas and other managed sites is established and sustained (Article III; AEWA Annex 3, para 3; Strategic Plan objective 3)
Output 7.1 | Site inventory: known sites of national or international importance for AEWA populations have been reviewed and confirmed (AEWA Annex 3, para 3.1; Strategic Plan target 3.1; Res. 8.6, 9.2 & 9.4)
Activity 7.1.1 | Facilitate the completion and submission by all Parties and other Range States of their national site inventories contributing towards the AEWA Flyway Site Network, including for seabirds (Res. 9.2, OP1.2(a) & Res. 9.4, OP1.7) | 3 | SD | Yes | ?
Activity 7.1.2 | Facilitate the update of the Critical Site Network Tool with the revised site information communicated by Parties and other Range States (Strategic Plan task 3.1(b); Res. 8.6, OP2) | 3 | SD | Yes | ?
Output 7.2 | Site status assessment: the status of, the threats to, and the effectiveness of conservation measures implemented at flyway network sites are being assessed at flyway scale, using data provided by Parties and other Range States (Strategic Plan target 3.2)
Activity 7.2.1 | Facilitate the development of a site monitoring system for submission to and adoption by MOP10 (Strategic Plan task 3.2(a); Res. 9.2, OP1.2(d)) (Linked to Activity 1.3.2) | 3 | SD | Yes | ?
Outcome 8 | Sufficient quantity and quality of habitat in the wider environment is ensured (Article III; AEWA Annex 3, para 3; Strategic Plan objective 4)
Output 8.1 | Habitat conservation priorities: priorities for habitat conservation and management in the wider environment are identified at Agreement level and corresponding actions are being implemented by the Parties (Strategic Plan target 4.1; Res. 9.2)
Activity 8.1.1 | Facilitate the compilation of an assessment of the status of principal waterbird habitats in the wider environment and the development of habitat action plans (Strategic Plan tasks 4.1(a)-(b); Res. 9.2, OP1.3(a)) | 3 | SD | Yes | ?
Outcome 9 | Parties are assisted in the implementation of the Agreement through the provision of conservation guidelines and other relevant guidance (Article IV; AEWA Annex 3, para 7.3)
Output 9.1 | Access to Conservation Guidelines and other guidance: Parties are provided with easy access to available AEWA guidelines and other adopted guidance (AEWA Annex 3, para 7.3; Res. 9.5, OP3 & 4)
Activity 9.1.1 | Disseminate revised Conservation Guidelines number 4 and 7 to all Range States, and relevant international governmental and non-governmental organisations, and promote and monitor their use to the extent that this is possible (Res. 9.5, OP3) (Linked to Activity 10.1.3) | 2 | ML, FK, DS, JD | No | 2026-05-01 | 2026-07-31 | 66 | bar: 2026-07-01
Activity 9.1.2 | Maintain an up-to-date online version of Appendix 1 to Res. 9.5 on the AEWA website (Res. 9.5, OP4) | 2 | ML, FK, DS, JD | No | 2026-05-01 | 2026-07-31 | 66 | bar: 2026-07-01
Outcome 10 | The implementation of the Agreement is supported by active communication, education and training, and awareness raising (Articles III & VIII; AEWA Annex 3, para 6; Res. 6.10 & 9.6)
Output 10.1 | Communication: relevant information is communicated regularly by the Secretariat (Article VIII; Res. 6.10)
Activity 10.1.1 | Maintain functional and up-to-date communication tools, such as the AEWA website and other necessary auxiliary websites, social media channels, and digital mailing lists, and disseminate relevant information through them following a communication plan and guided by the AEWA Communication Strategy (Article VIII(e) & (j); Res. 6.10, OP2) (Linked to Activity 10.1.2) | 1 | FK, DS, SD, ML, EPM, CL, BD, JD | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 10.1.2 | Continue to play a central role in the organisation of the World Migratory Bird Day (WMBD) campaign (Res. 9.6, OP4) (Linked to Activity 10.1.1) | 3 | FK, DS | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 10.1.3 | Publish and disseminate AEWA conservation guidelines and other guidance, as well as reports, plans and other pertinent papers, and disseminate to Parties and other relevant target groups (Article VIII(e); AEWA Annex 3, paras 7.3 & 7.4) (Linked to Activity 9.1.1) | 2 | FK, DS, SD, ML, EPM, CL, JD, BD | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Output 10.2 | CEPA: Communication, Education and Public Awareness (CEPA) activities are undertaken in a systematic and synergistic manner (Articles III & VIII; AEWA Annex 3, para 6; Res. 9.6)
Activity 10.2.1 | Secure the funding for and develop a CEPA Approach in line with Article III, paragraph 2 and Article VIII, paragraphs c, d, e & j (Res. 9.6, OP1 & 9) | 2 | FK, SD | Yes | 2026-06-01 | 2028-12-31 | 675 | bar: 2028-12-01
Activity 10.2.2 | Support CEPA Focal Points and strengthen their capacity by providing training, tools and templates for CEPA activities (Res. 9.6, OP8) | 3 | FK, DS | Yes | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 10.2.3 | Establish a network to help CEPA Focal Points share knowledge and expertise (Res. 9.6, OP8) | 3 | FK, DS | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 10.2.4 | Support CEPA National Focal Points, Technical Committee and the TC CEPA Expert in linking and promoting synergies with the programmes of other Multilateral Environment Agreements (MEAs) and Flyway Initiatives on CEPA, and with equivalent programmes and initiatives of other governmental and non-governmental bodies at international, regional, national and local levels (Res. 9.6, OP12) | 3 | FK, DS | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 10.2.5 | Develop a webpage to bring together and present TC-collated evidence on the effectiveness and good-practice case studies of successful and inspirational CEPA interventions conducted by Contracting Parties and other relevant actors (Res. 9.6, OP5) | 3 | FK, DS | No | ?
Outcome 11 | The Agreement is in force throughout the entire range of the AEWA area (AEWA Preamble)
Output 11.1 | Parties to the Agreement: the number of Contracting Parties has increased to at least 90 by MOP10 (Strategic Plan target 5.2)
Activity 11.1.1 | Liaise with non-Party Range States and promote and facilitate their accession to the Agreement working with the Standing Committee, other Parties and partner organisations (Article VIII(d)) | 1 | SD, CL, EPM, BD | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Outcome 12 | The Agreement and its Parties are served by the Secretariat in an effective and efficient manner within the limits of capacity and resources available (Article VIII)
Output 12.1 | Secretariat capacity and performance management: Secretariat’s staffing and its performance are well managed and coordinated (UN HR rules and regulations; Res. 9.9)
Activity 12.1.1 | Undertake continuous planning, monitoring, coordination, and management of the portfolio and the performance of the Secretariat and its staffing, including staff development (UN HR rules and regulations; Res. 9.9, OP5 & 23) | 1 | SD, ML, EPM, FK, CL, BL, MTK, JD, BD, DS, SH | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Output 12.2 | Routine administrative, office management and operational tasks: the Secretariat is proficient in delivering routine administrative, office management and operational tasks (UN admin rules and regulations; various mandates)
Activity 12.2.1 | Undertake routine administrative, office management and operational tasks, in a compliant, but efficient manner (UN admin rules and regulations; various mandates) | 1 | SD, ML, EPM, FK, CL, BL, MTK, JD, BD, DS, SH | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Output 12.3 | Assistance and advice to Parties: Parties receive competent assistance and advice (Article VIII)
Activity 12.3.1 | Provide assistance and advice to Parties on matters of the operations and implementation of the Agreement and its Strategic Plan and Plan of Action for Africa, as requested or as necessary, including, where feasible, facilitate coordination between Parties and with international and national organisations (Article VIII(d)) | 1 | SD, ML, EPM, CL, JD, BD | Partially | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-04-01 to 2028-07-01; 2028-12-01
Output 12.4 | Synergies and coordination with other MEAs and organisations: the implementation of the Agreement is undertaken in a synergistic and cooperative manner with other Multilateral Environmental Agreements (MEAs) and other relevant organisations (Article IX)
Activity 12.4.1 | Maintain regular contact with and consult with the Secretariats and governing and subsidiary bodies of CMS and other pertinent MEAs, as well as with other relevant organisations in respect of matters of common interest (Article IX(a)-(c)) | 1 | SD, ML, EPM, FK, CL | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Outcome 13 | UN and UNEP policies are facilitating efficient and effective operations of the Secretariat and the Agreement (Res. 9.9)
Output 13.1 | UN Staff Mobility Policy: the implementation of the UN Staff Mobility Policy strengthens the continuity of Secretariat staffing through retaining institutional knowledge, operational effectiveness, and maintaining competent institutional capacity and consistent quality of uninterrupted service delivery (Res. 9.9)
Activity 13.1.1 | Assist the StC in examining the implications of the UN Staff Mobility Policy for the Secretariat and the Agreement and submitting a report and recommendations to MOP10 (Res. 9.9, OP29) | 1 | SD, CL | Partially | 2027-08-01 | 2028-07-31 | 261 | bar: 2028-07-01
Output 13.2 | Partnership Policy: the UNEP Partnership Policy provides for effective and efficient operations of the Secretariat and the Agreement (Res. 9.9)
Activity 13.2.1 | Develop an AEWA partnership policy with associated procedures which are tailored to the Agreement’s activities and processes as per the allowance stipulated in the UNEP Partnership Policy for customised MEA-specific partnership policies (Res. 9.9, OP30) | 1 | SD, ML, EPM, FK, CL, BL, MTK, JD, BD, DS, SH | Yes | 2026-08-01 | 2028-07-31 | 521 | bar: 2028-07-01
Outcome 14 | The Secretariat operates with optimal and predictable funding and other resources (Articles V and VIII; Res. 9.9)
Output 14.1 | Financing: sufficient funding is provided and available for the highest priority tasks and deliverables assigned to the Secretariat (Articles V & VIII; Res. 9.8 & 9.9)
Activity 14.1.1 | Administer and manage trust fund 40AWL (assessed contributions), including collecting due annual assessed contributions and arrears, and emergency one-off replenishment contributions; maintaining the working capital at the set threshold; arranging for loans, as necessary and feasible; monitoring exchange rate fluctuations and adjusting levels of expenditure, where necessary (Articles V.2(a) & VIII(i); Res. 9.9, OP9-14 & 16) | 1 | SD, CL, EPM, MTK, BD | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 14.1.2 | Request and manage contributions towards trust fund 32AVL (voluntary contributions), and where possible voluntary contributions to trust fund 40AWL; where necessary, submit applications to various sources for raising voluntary monetary, or alternatively, in-kind contributions (Article VIII(i); Res. 9.9, OP17-19, 21) | 1 | SD, CL, ML, EPM, FK, BL, JD, BD, SH | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 14.1.3 | Submit to the Standing Committee periodic budget reports and estimates of expenditures for the following period (Article VIII(i); Res. 9.9, Appendix IV, para 17-19) | 1 | SD, CL, MTK | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 14.1.4 | Prepare and submit to MOP10 for consideration a series of budget scenarios for the following triennium (Res. 9.9, OP8 & 22, Appendix IV, para 12) | 1 | SD, CL | No | 2028-01-01 | 2028-07-31 | 151 | bar: 2028-03-01 to 2028-07-01
Output 14.2 | Capacity mobilisation: additional capacity is mobilised in support of the highest priority task and deliverables assigned to the Secretariat (Res. 9.8 & 9.9)
Activity 14.2.1 | Request Parties to allocate a Junior Profession Officer (JPO) for Technical Committee support as well as other JPOs or second gratis personnel (Res. 9.8, OP4 & 9.9, OP24) | 1 | SD, CL, ML | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Activity 14.2.2 | Invite governments, intergovernmental and non-governmental organisations and other sources to consider contributing to the implementation of the Agreement on a voluntary basis, particularly through in-kind contributions, such us human capacity (Res. 9.9, OP21) | 1 | SD, CL, ML | No | 2026-01-01 | 2028-12-31 | 782 | bar: 2028-12-01
Statuses
| Not started |  | ◄ Insert more rows to insert more statuses
In progress
Blocked
Complete
Quarter Names
| Q1 |  | Jan - Mar
| Q2 |  | Apr - Jun
| Q3 |  | Jul - Sep
| Q4 |  | Oct - Dec
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
Note on AL66: Evelyn Moloko (UNEP/AEWA Secretariat): As per the updated proejct document, the GCC activity is scheduled to end in Q1 of 2028. So it should be adjusted here.