15th MEETING OF THE TECHNICAL COMMITTEE

09–11 April 2019, Bonn, Germany

DRAFT TERMS OF REFERENCE FOR THE DEVELOPMENT OF MONITORING FRAMEWORK FOR THE AEWA FLYWAY SITE NETWORK

Introduction

Target 3.2 of the AEWA Strategic Plan 2019-2027 foresees that “the status of, the threats to, and the effectiveness of conservation measures implemented at flyway network sites are being assessed at flyway scale, using data provided by at least three-quarters of Contracting Parties”. Action a) to this target foresees that a framework for the AEWA flyway site network is developed by MOP8 (i) building on the preliminary Site Network Review presented to MOP5 and (ii) coordinated with similar reporting processes under multilateral processes, notably the Ramsar Convention on Wetlands, the EU Birds Directive and the Bern Convention Emerald Network. Based on this framework, Parties are expected to assess and report on the status of their flyway network sites by MOP9 and that the Technical Committee and the Parties produce a flyway-level assessment of the conservation status of flyway network sites by MOP10. This report would fulfill the functions of the international review on “the network of sites used by each population, including reviews of the protection status of each site as well as of the management measures taken in each case” required by Paragraph 7.4 of the AEWA Action Plan but not yet produced in the history of AEWA except the preliminary report presented to MOP5. A key lesson from the preliminary Site Network Review is that producing such reports requires that adequate site monitoring is in place in the Contracting Parties and they report on the status of sites.

1. Project title

Framework for the monitoring of the status of the threats to, and the effectiveness of, conservation measures implemented at flyway network sites

2. Background

Target 3.2 of the AEWA Strategic Plan 2019-2027 foresees that “the status of, the threats to, and the effectiveness of conservation measures implemented at flyway network sites are being assessed at flyway scale, using data provided by at least three-quarters of Contracting Parties”. Action a) to this target foresees that a framework for the AEWA flyway site network is developed by MOP8 (i) building on the preliminary Site Network Review presented to MOP5 and (ii) coordinated with similar reporting processes under multilateral processes, notably the Ramsar Convention on Wetlands, the EU Birds Directive and the Bern Convention Emerald Network.

3. Duties of the contractor

The contractor shall develop a technical proposal to the Technical Committee that covers the following issues:

    - Review site monitoring frameworks under the Ramsar Convention on Wetlands, the EU Birds Directive and the Bern Convention Emerald Network, the World Heritage Convention and other similar instruments, including interoperability of data and processes;

    - Framework for and technical guidance on assessing the status of flyway network sites;

    - Framework for and technical guidance on assessing the pressures and threats to flyway network sites;

    - Framework for and technical guidance on reporting on conservation measures implemented at flyway network sites and their effectiveness;

    - Proposal for data management and presentation on the Critical Site Network Tool.

4. Duration of the project (tentative dates)

A report on point (i) to be presented to the Technical Committee by May 2020.

Technical guidance on points (ii) - (iv) to Contracting Parties to be presented to the Technical Committee by January 2021.

Proposal for data management and presentation to be presented to the Technical Committee by January 2021

Following the review of the drafts by the Technical Committee (TC), the contractor will be expected to incorporate the views of the TC and produce and submit improved versions as required. Final draft to be submitted to the Secretariat by April 2021.