Project on Strengthening waterbird and wetland conservation capacities in North Africa (WetCap)

- budget situation as at 19 February 2010 -

| Activities | Estimated costs | Committed to BLI/SEO | Committed to BLI | AEWA (expected) expenditures | Expected expenditures e.g. for additional sub-contracts | Total (expected) expenditures/ commitments | Savings/ over-expenditures | State of Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1 |  |  |  |  |  |  |  |  |
| Regional workshop: Adaptation of the WOW training and awareness raising programme to the region | In progress |
| Travel and DSA for 20 experts | 40,000 | 37,500 |  | 1,250 | 1,250 | 40,000 |  |  |
| Renting of venue and equipment | 5,000 | 5,000 |  |  |  | 5,000 |  |  |
| Interpretation | 3,000 | 3,000 |  |  |  | 3,000 |  |  |
| Preparation of documents | 2,500 |  |  |  | 2,500 | 2,500 |  |  |
| Translation of documents | 2,500 |  |  |  | 2,500 | 2,500 |  |  |
| Sub-total | 53,000 | 45,500 | 0 | 1,250 | 6,250 | 53,000 | 0 |  |
| Regional adaptation of the training and awareness raising material | In progress |
| Meetings of the Training Board | 20,000 | 20,000 |  |  |  | 20,000 |  |  |
| Preparation of material | 15,000 | 2,000 | 943 |  | 12,057 | 15,000 |  |  |
| Sub-total | 35,000 | 22,000 | 943 | 0 | 12,057 | 35,000 | 0 |  |
| National adaptation of the training and awareness raising material in five countries | In progress |
| Preparation of material | 25,000 | 5,000 |  |  | 20,000 | 25,000 |  |  |
| Sub-total | 25,000 | 5,000 | 0 | 0 | 20,000 | 25,000 | 0 |  |
| Translation of relevant MEA documents | 26,000 |  | 25,800 |  |  | 25,800 |  | In progress |
| Sub-total | 26,000 | 0 | 25,800 | 0 | 0 | 25,800 | 200 |  |
| Sub-contracts (international and local partner organizations, external experts, local staff) | 40,000 | 0 | 40,377 |  |  | 40,377 |  | In progress |
| Sub-total | 40,000 | 0 | 40,377 | 0 | 0 | 40,377 | -377 |  |
| Component 1 total | 179,000 | 72,500 | 67,120 | 1,250 | 38,307 | 179,177 | -177 |  |

| Activities | Estimated costs | Committed to BLI/SEO | Committed to BLI | AEWA (expected) expenditures | Expected expenditures e.g. for additional sub-contracts | Total (expected) expenditures/ commitments | Savings/ over-expenditures | State of Implementation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 2 |  |  |  |  |  |  |  |  |
| Regional workshop: Review of CSN tool data and identification of gaps | Finalized |
| Travel and DSA for 20 experts | 40,000 | 36,524 |  | 1,250 |  | 37,774 |  |  |
| Renting of venue and equipment | 5,000 | 5,000 |  |  |  | 5,000 |  |  |
| Interpretation | 3,000 | 3,000 |  |  |  | 3,000 |  |  |
| Preparation of documents | 2,500 |  | 2,945 |  |  | 2,945 |  |  |
| Translation of documents | 2,500 |  |  |  |  |  |  |  |
| Component 2 total | 53,000 | 44,524 | 2,945 | 1,250 | 0 | 48,719 | 4,281 |  |
| Overarching activities |  |  |  |  |  |  |  |  |
| Steering Committee meetings (yearly, 6 members) | 15,000 | 11,387 | 1,178 | 2,500 |  | 15,065 |  | 1st meeting finalized; 2nd in progress |
| Project coordination (overall supervision, financial management and implementation) | 40,000 |  |  | 40,000 |  | 40,000 |  | In progress |
| Regional coordination (support implementation of activities) | 45,000 | 45,000 |  |  |  | 45,000 |  | In progress |
| Development of project website | 6,500 |  |  | 6,500 |  | 6,500 |  | Finalized |
| Development and production of project information material (brochures, posters, leaflets, e-newsletter etc.) | 10,000 |  |  | 10,000 |  | 10,000 |  | In progress |
| Administration and general costs (mailings, communication, reporting requirements travel on official business, office supplies) | 10,000 | 4,000 |  | 6,000 |  | 10,000 |  | In progress |
| Contingencies | 2,000 |  |  | 2,000 |  | 2,000 |  |  |
| Overarching activities total | 128,500 | 60,387 | 1,178 | 67,000 | 0 | 128,565 | -65 |  |
| TOTAL ACTIVITIES COSTS | 360,500 | 177,411 | 71,243 | 69,500 | 38,307 | 356,461 | 4,039 |  |
| 13 % overhead | 46,865 | 23,063 | 9,262 | 9,035 | 4,980 | 46,340 | 525 |  |
| TOTAL PROJECT COSTS | 407,365 | 200,474 | 80,505 | 78,535 | 43,287 | 402,801 | 4,564 |  |