| WETCAP WORKPLAN (version updated in February 2010) |
| --- |
| ACTIVITY | LEADING ORGANIZATION | COMMENTS |
| 2009 |  |  |
| March - mid-June |  |  |
| 1. Prepare SSFA with project partners | AEWA and partners | BLI/SEO & BLI done |
| 2. Launch project with press release | AEWA and partners | Done |
| 3. Develop work plan | AEWA and partners | Done |
| June |  |  |
| 1. Recruitment of Regional Coordinator | SEO | Done |
| 3. Introduce Regional Coordinator to AEWA network via e-news | AEWA | done; e-news inform about WetCap regularly |
| July |  |  |
| 1. Develop project webpage (on AEWA website) | AEWA | Done |
| 2. Start translations of key documents into Arabic | BLI | Ongoing |
| 3. Establish database of relevant contacts of experts, institutions etc. in all project countries | SEO | Done |
| August |  |  |
| 1. 1st Steering Committee meeting | SEO, AEWA and partners | Took place on 25/08/09, UN Campus, Bonn, Germany |
| a) logistical preparation (venue, equipment, travel, accommodation etc.) | SEO | Done |
| b) preparation of documents | AEWA and partners | Done |
| 2. 9-19/8: Amman TOT |  | It was decided not to send Egyptian participants |
| 3. Finalize project webpage and circulate link to partners for comments | AEWA | Done |

| September |  |  |
| --- | --- | --- |
| 1. Letter to Focal Points to introduce Regional Coordinator; inform about activities in Year 1 and ask for contact details of experts to be involved in project countries | SEO, AEWA | Done |
| 2. Look into possibilities of establishing a project Intranet | SEO | e.g. www.ning.com; to be further discussed with AEWA Information Officer; ongoing |
| 3. Develop Guidelines and application and assessment forms for WetCap Small Grants Fund on basis of AEWA SGF & comments received at the 1st Steering Committee meeting; circulate to the Steering Committee for comments and approval | AEWA | Done |
| 4. Meet donor to discuss funding of Year 2 and contract for Year 1 and 2 | AEWA | Done |
| 5. Produce overview of projects, initiatives, potential partners in the region | AEWA | Ongoing |
| October |  |  |
| 1. Regional workshop to review CSN tool | BLI, WI, SEO | Workshop took place on 3-5 December 2009 |
| a) identification and invitation of participants; logistical preparation (venue, equipment, travel, accommodation etc.) | SEO |  |
| b) preparation of documents | BLI, WI |  |
| c) delivery of the workshop | BLI, WI |  |
| 2. Development of project brochure and roll-up banner | AEWA, SEO | Both should contain general information to raise awareness on WetCap; roll-up banner to be produced for each partner; brochure has been drafted, but finalisation of activity was postponed for financial reasons |
| November |  |  |
| 1. Dakar TOT | SEO | Mauritania atttended with support from WOW; Tunisia, Algeria and Morocco attended with support from WetCap (1 participant/ country) in order to maximize the effect of the Wetcap ToT in 2010 |
| 2. 30/11: Progress report from SEO to AEWA | SEO |  |
| December |  |  |
| 1. Call for tender for WetCap SGF | AEWA |  |
| 2. Progress report to donor | AEWA |  |

| 2010 |  |  |
| --- | --- | --- |
| January |  |  |
| 1. 1-day meeting of Training Board | SEO, BLI | To involve Ibrahim Khader, BLI Middle East; Training Board should consist of 1-2 experts from each country; in preparation |
| a) identification and invitation of participants; logistical preparation (venue, equipment, travel, accommodation etc.) | SEO |  |
| b) preparation of documents | BLI |  |
| c) delivery of the workshop | BLI |  |
| 2. Follow-up: adaptation process in the region/ countries | SEO, Training Board | Deadline for this process to be fixed at the Training Board meeting with view to the TOT workshop scheduled in 2010 |
| February |  |  |
| 1. Review and pre-assess applications for SGF | AEWA | To be presented to the 2nd Steering Committee meeting for final assessment and selection; activity postponed for financial reasons |
| 2. 2nd Steering Committee meeting | SEO | Last week of February, Rabat, Morocco; in preparation |
| April |  |  |
| 1. Prepare Year 2: SSFAs, work plan etc. | AEWA and partners |  |
| July |  |  |
| 1. 31/7: Final report from BLI to AEWA | BLI |  |
| 2. 31/7: Final report from SEO to AEWA | SEO |  |
| August |  |  |
| 1. Final report from AEWA to AECID | AEWA |  |

Activities Year 2 in brief:

1. Regional Training of trainers

2. Based on the CSN tool workshop:   2 surveys per country

2 monitoring field missions per country

3. Selection and starting implementation of 2 local projects per country